## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Anusha Hamy: 23594256
As a user, I want:
|  | No | User stories
|  | 1 | to create snake game
|  | 2 | the game board needs to look like black colour board.
|  | 3 | to have 1 snake in game
|  | 4 | move the snake
|  | 5 | the game have 1 prey
|  | 6 | have apple as prey
|  | 7 | use arrow keys to change the directions of snake
|  | 8 | to enter username and password to enter the game
|  | 9 | locate an apple in game board in random location
|  | 10 | snake to eat an apple
|  | 11 | grow the legth of the snake
|  | 12 | display game over
|  | 13 | die snake when, snake hits the wall or itself.

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Anusha Hamy: 23594256
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard
3.1.2 |  |  | GUI for login form
3.1.3 |  |  | GUI layoutmanager
3.1.4 |  |  | Load Images to GUI
3.2 |  | Build the game logic
3.2.1 |  |  | Snake logic
4 | Test and deploy the game |  |  | 3 | 30%
4.1 |  | Test the login |  |  | 100%
4.2 |  | Test the gameboard |  |  | 50%
5 | Document the game |  |  | 4 | 0%